## Sprint Backlog
Story ID | Title | Task | Initial Effort (Hrs) | Day 1Remaining(hrs) | Day 2 Remaining(hrs) | Day 3 Remaining(hrs)
US01 | User Auth | Login/Registration API | 6 | 2 | 2 | 2
US02 | Role Access | Clerk/Inspector/Super/Driver logic | 4 | 2 | 2 | 0
US03 | Driver Onboard | Register Driver with Validation | 5 | 1 | 3 | 1
US04 | License Logic | Issue/Expire/Deactivate licenses | 6 | 2 | 2 | 2
US05 | Vehicle Reg | Map vehicle to driver | 5 | 3 | 2 | 0
US06 | Tax Engine | Tax calculation + penalty | 5 | 1 | 1 | 3
US07 | Violation Entry | Inspector ticket entry | 5 | 1 | 2 | 2
US08 | Fine Payment | Payment + penalty logic | 4 | 2 | 2 | 0
US09 | Renewal | Driver request & Approval | 4 | 2 | 1 | 1
US10 | Reminders | Tax/License alerts | 4 | 2 | 1 | 1
US11 | Compliance | Non-compliance flagging | 4 | 2 | 2 | 0
US12 | Delete Service | Status updates | 3 | 1 | 1 | 1
US13 | Reporting | Violation filtering | 4 | 1 | 3 | 0
US14 | Dashboard | Revenue calculation | 3 | 1 | 1 | 1
US15 | Audit Log | System activity logs | 3 | 2 | 1 | 0
Inital estimation trend |  |  | 70 | 25 | 26 | 19
Actual estimation trend |  |  | 65 | 25 | 26 | 14

## Burndown Chart
Day | Ideal Effort | Actual Effort
Day 0 | 70 | 65
Day 1 | 25 | 25
Day 2 | 26 | 26
Day 3 | 19 | 14